# Check-In with Paul

July 10, 2026  |  Aditi Kalle

## Since your last report

- ERA5 comparison done. r=0.194 with panel_w (weak). Shifting to NOAA.

- Scheduler prototype works end-to-end. Test run picked 29 of next 48 hours, all daylight.

- IMTA system retrieved. Data closed at 41 days (May 20 to June 30).

- Met with Jack July 9. Pivoting to data-first: variable selection and prep is ~90% of the work, model choice ~10%.

## Next 2 weeks (Jack at retreat)

- Data exploration: correlations, redundancy, quality on the 41-day CSV

- NOAA weather research for the buoy's coordinates

- Re-scope lit review for variables used, not architectures

- Paper review session with Jack after retreat

## For you

- 41 days final. Realistic for 1-week forecast?

- Weather sources beyond NOAA worth trying near the deployment?

- Does the pivot read right with ~2.5 to 3 months left?