# Research Highlights

IMTA Marine Energy Fellowship

Aditi Kalle  |  For: Mitchell Scott  |  July 2026  |  20-min Brief

## Fellowship Roadmap Update (May 26 → July 14)

May 26 direction: IMTA at the applied level. Research questions for different solar and battery configurations. Lit review → Tools/SOTA → Implementation → Relevance to current work.

June progress: Built forecasting pipeline and 11-model benchmark on live buoy data. Learned that simple baselines (Naive Seasonal) dominate small datasets; ML advantage emerges with more history.

July pivot: Realized "which model wins?" was the wrong question. Real bottleneck is data preparation and variable selection (90% of effort), not algorithm choice (10%). Methodology now data-first, not model-first.

## Concrete Deliverables

| Deliverable | Status | Result |
| --- | --- | --- |
| Data pipeline | ✓ Complete | 41 days (121K records), cloud → CSV, clean and validated |
| 11-model benchmark | ✓ Complete | Naive Seasonal MAE 0.72 W (Jun 14), SVR 4.14 W (Jun 24); ML advantage clear by day 35 |
| Camera scheduler | ✓ Working | Integer LP, 48-hour horizon, battery-safe; 100% uptime under normal solar |
| Hardware lessons | ✓ Documented | 5 failure modes (connectors, fouling, mounting); fixes prioritized for next deployment |
| Methodology framework | ✓ Learned | 90% data / 10% model; how to read papers for variables, not architectures |
| Lit review | In progress | 10 of 22 papers read; re-scoped to focus on variable selection and data quality |

## Key Finding: Ceiling on Model Performance

Evidence: Across three data pulls (Jun 4, 14, 24), model accuracy improved, but differences narrowed to fractional watts (0.72 W to 4.14 W MAE). By Jun 24, the top two models sat within 0.1 W of each other despite architectural differences.

Figure 1: solar forecast accuracy across three data pulls. All four models converge to a narrow band by Jun 24.

Interpretation: With current inputs (panel_w, batt_v, basic forecasting), we're hitting the ceiling of what models can achieve. Better algorithms won't close the gap. Better inputs will.

Action: Shifted to data exploration: NOAA vs. ERA5, variable correlations, what's redundant.

## The Methodology Shift (June → July)

June approach: Benchmark models, show ML advantage, pick winner.

Issue: Felt inconclusive. Fractional-watt differences. Unclear which model to deploy.

July insight (Jack Mead, ML engineer): Model choice is easy; data preparation is hard. Focus on:

- What variables actually matter?

- What's correlated or redundant?

- How clean are the inputs?

- What's the physical constraint?

Figure 2: where the effort goes in the new methodology. Data preparation and variable selection is the focus; model choice is downstream.

New lit review lens: Papers that discuss variable selection are actionable. Papers that just say "we used LSTM and got 95% accuracy" are noise.

## Current Status and Path Forward

What we have:

- 41 days of hourly telemetry (May 20 to June 30)

- Working scheduler (deployed logic)

- Framework for data-first analysis

What we're doing (July to August):

- Data exploration: IMTA CSV correlations, outliers, missing data, redundancy

- Weather research: NOAA APIs vs. ERA5; local weather stations near the site

- Lit review (new lens): Extract what variables matter, data quality discussions

- Paper review sessions: With Jack, learn to critique papers for actionable insights

Constraint: IMTA system retrieved in July. No new data after June 30. Working with 41 days as the fixed dataset; quality of analysis matters more than data quantity.

## Research Contribution

Research gap confirmed: No published paper combines off-grid solar forecasting, adaptive duty-cycle scheduling, and marine IMTA deployment.

This fellowship's contribution: Not "best model wins" but "rigorous data analysis explains why model choice matters less than variable selection."

Practical implication: Documented methodology that's repeatable for other deployments: (1) collect data, (2) understand variables, (3) pick appropriate model. Not: (1) try 11 models, (2) hope one works.

## Open Questions for Discussion

- Data sufficiency: 41 days for a 1-week forecast. Adequate for other IMTA sites, or should we prioritize finding historical weather archives?

- Variable scope: Beyond panel_w and batt_v, what other sensor data would improve predictions? Wind? Humidity? Cloud cover inferred from other sources?

- Next deployment hardware: Any planned upgrades that affect sensor fidelity or logging granularity?